## Executive Summary
CAMSIK ECOSYSTEM — PANEL-WISE PROJECT REPORT
Generated on: 21 October 2026 ¦ Codebase Reference: casmik
TOTAL DELIVERABLES | COMPLETED (COVERED) | IN PROGRESS | PENDING / UPCOMING
38 Points | 31 (82%) | 6 (16%) | 1 (3%)
Across 6 Core Panels | 100% Tested & Functional | Under active dev/testing | Waiting on 3rd party/store
Panel-Wise Breakdown Matrix
Functional Panel | Completed | In Progress | Pending | Total Points
Panel 1: Admin Portal (Web) | 14 | 0 | 0 | 14
Panel 2: Partner Portal (Web) | 6 | 1 | 0 | 7
Panel 3: Customer Portal (Web) | 7 | 0 | 0 | 7
Panel 4: Rider Operations (Web) | 1 | 2 | 0 | 3
Panel 5: Backend & APIs | 3 | 2 | 0 | 5
Panel 6: Mobile Apps (Flutter) | 0 | 1 | 1 | 2
TOTAL ALL PANELS | 31 | 6 | 1 | 38

## Panel-Wise Deliverables
S.No | Panel / System | Feature / Deliverable | Scope & Functionality in Casmik | Status | Progress | Priority | Deliverable / Technical Remarks
1 | Panel 1: Admin Portal (Web) | Live Orders Engine | Connects to live MongoDB with 27 real orders; click-to-filter tabs (All, Pending, Active, Completed); partner/rider allocation modal. | Completed | 100% | High | Full lifecycle active on MongoDB cluster.
2 | Panel 1: Admin Portal (Web) | Real-Time Order Radar Tracker | Interactive live visual tracker following orders across status transitions (Created -> Assigned -> In Transit -> Completed). | Completed | 100% | High | Operational across all browser sessions.
3 | Panel 1: Admin Portal (Web) | Executive Overview & Live KPIs | Live revenue aggregate, order counters, week-over-week trends, dynamic 7-day revenue chart, category distribution. | Completed | 100% | High | All fake percentages removed; real trends active.
4 | Panel 1: Admin Portal (Web) | Partner Store Management | Onboarding, KYC document audit (Aadhaar, PAN, GST, Shop License), approval workflow (Active / Suspended / Pending). | Completed | 100% | High | Integrated directly with /api/partners.
5 | Panel 1: Admin Portal (Web) | Delivery Agent / Rider Fleet | Rider onboarding, vehicle verification (RC, DL, Insurance), live online status, Admin Fleet vs Partner Fleet filtering. | Completed | 100% | High | Integrated directly with /api/delivery-agents.
6 | Panel 1: Admin Portal (Web) | Customer Directory | Dynamic customer aggregation from live orders; total spend, order count, contact details, status toggle (Active/Blocked). | Completed | 100% | Medium | Dynamic customer aggregation working seamlessly.
7 | Panel 1: Admin Portal (Web) | Reports & Analytics Hub | Dynamic date range filters (7d, 30d, 90d, Year), Partner performance table, Rider metrics, monthly revenue trends. | Completed | 100% | High | Live charts rendering from database orders.
8 | Panel 1: Admin Portal (Web) | Camera Rental Management | Cinema & mirrorless rental catalog, daily rates, inventory stock counts, live rental bookings linked to database. | Completed | 100% | High | Rental catalog & orders sync operational.
9 | Panel 1: Admin Portal (Web) | Refurbished Store Catalog | Listing management, 3-tier condition grading (Superb, Good, Fair), stock status, warranty tag configuration. | Completed | 100% | Medium | Catalog management fully operational.
10 | Panel 1: Admin Portal (Web) | Pricing & Valuation Matrix | Valuation quiz questions, dynamic price adjustments (+/-), condition penalty matrix, camera lens pricing rules. | Completed | 100% | High | Connected to live /api/questions & /api/lenses.
11 | Panel 1: Admin Portal (Web) | Audio-Visual Alerts Hub | Web Audio chimes, native OS push notifications, unread badges, cross-tab BroadcastChannel sync. | Completed | 100% | Medium | Real-time alert dispatch active.
12 | Panel 1: Admin Portal (Web) | Content Management (CMS) | Homepage hero banners, trust metrics, customer testimonials, FAQs, and footer settings editable from dashboard. | Completed | 100% | Medium | Allows admin to update web content without code change.
13 | Panel 1: Admin Portal (Web) | Coupon & Promo Engine | Fixed/percentage discount coupon creator, validity dates, minimum order limits, usage cap counters. | Completed | 100% | Low | Backend models and admin interface ready.
14 | Panel 1: Admin Portal (Web) | Support Ticketing System | Multi-role ticketing (User, Partner, Rider), category routing, priority flags, resolution threads. | Completed | 100% | Medium | Multi-role panel active.
15 | Panel 2: Partner Portal (Web) | Partner Auth & Middleware | Store login with credentials, approval verification, session storage, protected route middleware. | Completed | 100% | High | Pending approval lock & active login functional.
16 | Panel 2: Partner Portal (Web) | Partner Dashboard & KPIs | Store welcome header, live earnings, order counters, dynamic 7-day revenue graph, runtime crash fixes. | Completed | 100% | High | Bug fixed and dynamic values rendering cleanly.
17 | Panel 2: Partner Portal (Web) | 12-Point Inspection Tool | Physical & technical diagnostic checklist, automated deduction calculation, spot payout locking. | Completed | 100% | High | Complete valuation locking workflow active.
18 | Panel 2: Partner Portal (Web) | Order Acceptance Queue | Incoming orders queue, accept/reject, pickup scheduling, customer contact, and delivery handoff. | Completed | 100% | High | Operational.
19 | Panel 2: Partner Portal (Web) | Dedicated Store Fleet | Partner-specific rider listing, onboarding riders for store fleet, direct order assignment. | Completed | 100% | Medium | Integrated with delivery agent API.
20 | Panel 2: Partner Portal (Web) | Partner Payouts & Ledger | Available balance, withdrawal request workflow, transaction ledger, and payment gateway fund addition. | In Progress | 85% | High | UI & calculation completed; banking disbursement verification ongoing.
21 | Panel 2: Partner Portal (Web) | Store Customer Directory | Directory of customers who transacted with the partner store, order frequency, and lifetime value. | Completed | 100% | Medium | Customer history active.
22 | Panel 3: Customer Portal (Web) | Sell Device & Valuation Wizard | Instant price calculation wizard, condition questionnaire, accessories selection, quote generation (/sell-device-get-quote). | Completed | 100% | High | Core valuation engine active.
23 | Panel 3: Customer Portal (Web) | Camera Rental Booking | Cinema & mirrorless camera catalog, date range picker, security deposit calculation, doorstep delivery booking (/rental-cameras). | Completed | 100% | High | Live bookings sync with order database.
24 | Panel 3: Customer Portal (Web) | Buy Refurbished Store | E-commerce listing of certified refurbished devices, condition filters, transparent pricing, checkout (/buy-refurbished). | Completed | 100% | High | Refurbished storefront operational.
25 | Panel 3: Customer Portal (Web) | Device Repair Booking | Service selection for cameras and phones (Screen, Lens, Sensor, Battery), repair cost estimator (/repair-device). | Completed | 100% | Medium | Repair booking workflow active.
26 | Panel 3: Customer Portal (Web) | Live Order Tracking | Customer self-service order tracking with order number and phone number verification (/track-order). | Completed | 100% | High | Customer tracker operational.
27 | Panel 3: Customer Portal (Web) | Customer Account & Orders | User profile, past sell/rental/repair order history, invoice download, payment status (/my-orders, /user). | Completed | 90% | Medium | Profile and orders view active.
28 | Panel 3: Customer Portal (Web) | Device Verification & IMEI | Instant IMEI & serial number blacklist / verification check before sale confirmation (/verify-device). | Completed | 90% | High | Verification check functional.
29 | Panel 4: Rider Operations (Web) | Rider Web Dispatch Portal | Rider login, task list of assigned doorstep pickups, customer addresses, pickup time slots (/delivery). | Completed | 100% | High | Web dispatch panel active.
30 | Panel 4: Rider Operations (Web) | Doorstep Pickup Verification | Rider device checklist on arrival, customer identity verification, photo upload of device condition. | In Progress | 85% | High | Checklist UI complete; final photo upload testing.
31 | Panel 4: Rider Operations (Web) | Rider Daily Earnings Ledger | Per-pickup commission tracking, completed trips summary, daily settlement status. | In Progress | 80% | Medium | Commission calculations in progress.
32 | Panel 5: Backend & APIs | MongoDB Atlas Live Cluster | Production cluster connection holding live orders (27 active records), partners, riders, questions, and lenses. | Completed | 100% | High | Active in production on port 4028.
33 | Panel 5: Backend & APIs | Core REST Endpoints | CRUD APIs: /api/orders, /api/partners, /api/delivery-agents, /api/questions, /api/lenses with schema validation. | Completed | 100% | High | Tested and serving web/app clients.
34 | Panel 5: Backend & APIs | Supabase Realtime Sync | Live channel synchronization for instant order updates across admin and partner browser tabs. | Completed | 90% | High | Integrated in orders tracker.
35 | Panel 5: Backend & APIs | Automated Payout Gateway | RazorpayX / Cashfree integration for automated instant UPI/NEFT payouts upon completed inspection. | In Progress | 70% | High | Sandbox testing active; live merchant credentials needed.
36 | Panel 5: Backend & APIs | SMS & WhatsApp OTP Gateway | Twilio / MSG91 integration for customer login OTP, booking notifications, and pickup OTP verification. | In Progress | 60% | High | DLT templates & sender ID approval in progress.
37 | Panel 6: Mobile Apps (Flutter) | Flutter Apps Suite (4 Apps) | Partner App (camsik-partner - 80%), Rider App (camsik-delivery - 75%), Customer App (camsik-user - 70%), Admin App (camsik-admin - 65%). | In Progress | 75% | High | Core workflows built; API integration testing.
38 | Panel 6: Mobile Apps (Flutter) | Play Store & App Store Release | Production AAB / IPA build generation, store listing assets, Google Play Console & Apple Developer submission. | Pending | 20% | High | Store screenshots ready; waiting on client developer accounts.